## Carbondale Test Hole #1
CLEER DOE Project-Carbondale
520 South 3rd St
Carbondale, CO 81623
DRILLING LOG - Test Borehole #1
Date(s): 16 Nov 23 to 20 Nov 23
Location: | Legal | [5 empty] | Approx. Address: | 520 South 3rd St
| GPS | N39.39493 W107.20959 | [5 empty] | Carbondale, CO 81623
| Elevation | 6218' (GPS)
Driller: | PanTerra
State License #: | [6 empty] | Joints on rig: | 26 x 20' Joints
Rig:
Drilling Fluid: | Mud
Loop: | HDPE 1000' (500/500)
Grout: | TG Lite / PowerTEC (2:1) | [5 empty] | Rotary: | 4' GL to top of Tbl
SPUD/TD: | 520' | [6 empty] | 520' total reach
Spud with: | 8" tricone roller to 40' ¦ 5 5/8" tricone roller to 120' ¦ 5 5/8" PDC to 520'
Surface Water: | None
NOTE: Time gaps represent connections or unrelated activity.
Time |  | Activity | Duration | Depth (Ft.) |  |  | Comments
Start | End |  | Hrs:Min | From | To
2023-11-16 | [6 empty] | setup, warmup, mixed mud
7:37 | 7:40 |  | 0:03 | 0 | 10 | Unstable area, solved with casing | very coarse sand, granules (80/20), angular to subround, varied in color
7:40 | 8:09 |  | 0:29 | 11 | 20 |  | granules, v coarse sand, coarse sand, gravel (pebbler/cobble) (50/35/10/5), angular to subround (lots of mud lost to this region according to driller)
8:09 | 8:32 |  | 0:23 | 21 | 30 |  | AA, cobble/boulders encountered (~25' was problematic)
8:32 | 9:00 |  | 0:28 | 31 | 40 |  | gravel (cobble/boulder), granules, v coarse to fine sand, silt (40/40/15/5), color mainly grey
9:00 | 9:16 |  | 0:16 | 41 | 50 |  | AA
9:16 | 9:32 |  | 0:16 | 51 | 60 |  | AA
9:32 | 9:50 |  | 0:18 | 61 | 70 |  | AA, more silt, less sandy(40/40/10/10), ~50% limestone (LS)
9:50 | 10:03 |  | 0:13 | 71 | 80 |  | AA, ~75% LS
10:03 | 10:18 |  | 0:15 | 81 | 90 |  | AA
10:18 | 10:29 |  | 0:11 | 90 | 100 |  | AA more gravel, less sand (60/20/10/10), ~50% LS
10:29 | 10:43 |  | 0:14 | 101 | 110 |  | granules, clay, v. coarse sand to silt (50/30/20)
10:43 | 11:05 |  | 0:22 | 111 | 120 |  | clay, medium to fine grain sand, coarse sand (50/35/15) (seated casing, SDFN)
2023-11-17 | [6 empty] | reseated casing, setup, warmup, mixed mud
8:05 | 8:19 |  | 0:14 | 121 | 130 |  | pebbles, v. coarse sand to silt (50/50), ~25% LS (reduction in LS fraction may be due to non-LS cuttings settling in hole overnight)
8:19 | 8:27 |  | 0:08 | 131 | 140 |  | AA
8:27 | 8:33 |  | 0:06 | 141 | 150 |  | AA
8:33 | 8:38 |  | 0:05 | 151 | 160 |  | light grey to off white LS, high confidence we are in bedrock at this point.
8:38 | 8:45 |  | 0:07 | 161 | 170 |  | AA
8:45 | 8:50 |  | 0:05 | 171 | 180 |  | AA
8:50 | 8:56 |  | 0:06 | 181 | 190 |  | AA
8:56 | 9:01 |  | 0:05 | 191 | 200 |  | AA
9:01 | 9:09 |  | 0:08 | 201 | 210 |  | AA
9:09 | 9:14 |  | 0:05 | 211 | 220 |  | AA
9:14 | 9:23 |  | 0:09 | 221 | 230 |  | AA
9:23 | 9:30 |  | 0:07 | 231 | 240 |  | AA
9:30 | 9:34 |  | 0:04 | 241 | 250 |  | AA
9:34 | 9:38 |  | 0:04 | 251 | 260 |  | AA
9:38 | 9:45 |  | 0:07 | 261 | 270 |  | AA
9:45 | 9:51 |  | 0:06 | 271 | 280 |  | AA
9:51 | 9:57 |  | 0:06 | 281 | 290 |  | AA
9:57 | 10:01 |  | 0:04 | 291 | 300 | possible unstable shale in nearby sites | friable black carbonaceous shale/coal and darker grey LS (90/10)
10:01 | 10:07 |  | 0:06 | 301 | 310 |  | AA
10:07 | 10:11 |  | 0:04 | 311 | 320 |  | AA (50/50)
10:11 | 10:18 |  | 0:07 | 321 | 330 |  | AA
10:18 | 10:22 |  | 0:04 | 331 | 340 |  | AA
10:22 | 10:28 |  | 0:06 | 341 | 350 | unstable shale | AA (loop stuck on way down first try)
10:28 | 10:31 |  | 0:03 | 351 | 360 |  | AA (bit stuck on way up)
10:31 | 10:37 |  | 0:06 | 361 | 370 | possible unstable shale in nearby sites | AA
10:37 | 10:45 |  | 0:08 | 371 | 380 |  | AA
10:45 | 10:52 |  | 0:07 | 381 | 390 |  | AA
10:52 | 11:00 |  | 0:08 | 391 | 400 |  | AA (20/80)
11:00 | 11:05 |  | 0:05 | 401 | 410 |  | AA
11:05 | 11:12 |  | 0:07 | 411 | 420 |  | AA
11:12 | 11:19 |  | 0:07 | 421 | 430 |  | AA
11:19 | 11:27 |  | 0:08 | 431 | 440 |  | AA
11:27 | 11:34 |  | 0:07 | 441 | 450 |  | AA (10/90) (loop stuck on way down second try)
11:34 | 11:41 |  | 0:07 | 451 | 460 |  | AA
11:41 | 11:50 |  | 0:09 | 461 | 470 |  | Dark grey micritic LS (no shale noted)
11:50 | 11:58 |  | 0:08 | 471 | 480 |  | AA
11:58 | 12:07 |  | 0:09 | 481 | 490 |  | AA
12:07 | 12:21 |  | 0:14 | 491 | 500 |  | AA (lighter grey, similar to 150-290')
2023-11-18 | [6 empty] | Repaired mud pump, setup, warmup, mixed mud
11:10 | 11:15 |  | 0:05 | 501 | 510 |  | AA (some black shale present,may be due to cuttings settling in hole overnight)
11:15 | 11:20 |  | 0:05 | 511 | 520 |  | AA
|  |  |  | 521 | 530
|  |  |  | 531 | 540
|  |  |  | 541 | 550
|  |  |  | 551 | 560
|  |  |  | 561 | 570
|  |  |  | 571 | 580
|  |  |  | 581 | 590
|  |  |  | 591 | 600
|  |  |  | 601 | 605
| Total Drilling Time: |  | 7:54 | Hrs:Min |  | Drilling 0 - 520'
COMMENTS: | (16NOV) Gravel in the upper 40' of hole caused concern to driller, casing installed after drilling 120' (POOH). Casing consisted of 2x20' 6" dia Cresline HDPE, top ~4.5' were cut after insertion (~35' casing). Casing would not stay seated so drillers packed more hole plug (total 2 bags) and SDFN to allow to set overnight. (17NOV) Casing reseated with more hole plug (5 addtl bags) and drilling continued without issue to 500'. Drillers experienced difficulty pulling string at 400' and bit was stuck at ~360' for remainder of day - the mud pump had reduced circulation and driller believed cuttings accumulated atop the bit on the way down. (18NOV) Mud pump repaired and hole redrilled extending an additional 20' (520' total). Initial attempt to install loop failed ~350' due to debris / narrowing in hole. Redrilled hole to 520'. Second attempt got loop to 450', trimmed ~4 feet above ground, ends melted shut, tied to metal stake, and grouted with 20 bags of TG Lite and 10 bags of PowerTEC. (20NOV) Grout settled to 18' below surface (within casing), drillers backfilled with mudchips, cleaned up, and vacated site. Summary notes: 40 to 60' in adjacent areas may require casing due to unstable ground and large hard rock gravels (granite, basalt). This driller widened the hole to 8" down to 40' and installed 2x20' sections of locally sourced 6" dia Cresline HDPE and sealed with 3/8" bentonite hole plug. Production drillers may consider bringing preferred casing/hole plug to site as local supply/variety could be limited. 300' to TD may contain unstable carbonaceous shale lenses in adjacent areas, loop depths may vary within this range although head driller said he is confident 450' loop depth is achievable at scale. Drilling crew were helpful, hard working, and a pleasure to work with. They spoke highly of their company and were happy with the equipment they were using. Head driller notes: Clarity on mud/cutting disposal prior to arriving at site would have been helpful and allowed them to coordinate disposal option prior to arrival. This could cause delays for future exploratory holes depending on local disposal options.

## Legend
Geothermal Soil Analysis
LEGEND
Colors: | Descriptors: | Lithology: | Drilling:
blk - black | ang - angular | bas - basalt | AA - As Above
blu - blue | cmt - cement | bdl - boulder | PU - Pick Up
brn - brown | crs - coarse | cbl - cobble | POOH - Pull out of hole
bu - buff | dk - dark | cche - caliche | RIH - Run in hole
clr - clear | f - fine | cgl - conglomerate | RU - Rig Up
crm - cream | frm - firm | cl - clay | SDFN - Shut down for night
gn - green | hd - hard | dol - dolomite | SX - Sack(s)
gry - gray | L - Large | grt - granite | TD - Total Depth
pk - pink | lt - light | grvl - gravel
rd - red | M - Medium | ls - limestone
tn - tan | mtrx - matrix | qtz - quartzite
trnsl - translucent | S - Small | sd - sand
wh - white | sbang - sub angular | sh - shale
yel - yellow | sft - soft | slt - silt
| tr - trace | slts - siltstone
| uncons - unconsolidated | ss - sandstone
volc - volcanics