## Sheet1
Station | DAS | Install date | Demob date | Demob Comments | #files | conversion errors | # folders (days) | total data folder (GB) | Gap? | File Conversion Comments | MP Ch1 | MP Ch2 | MP Ch3 | Bubble Level | North azimuth
Mf11 | SMART24 | 2016-06-16 | 2016-11-02 | Vault had mouse tunnels at bottom. Active logging | 2228 | 1 | 94 | 3.4 |  | 20160921_100000 file damaged | 0.32 | -0.096 | -1.4 | center | N=N
Mf13 | SMART24 | 2016-06-16 | 2016-11-02 |  | 4460 |  | 94 | 2.83 |  | Files are half-hour | -4.1 | 4.89 | 1.67 | north inside ring | 352°
Mf32 | SMART24 | 2016-06-15 | 2016-11-02 |  | 2227 | 2 | 94 | 3.37 |  | 20160902_100000 & 20161009_1700 files damaged | 0.46 | -0.42 | -3.1 | center | N=N
Mf34 | SMART24 | 2016-06-17 | 2016-11-03 |  | 2254 |  | 95 | 3.45 |  |  | -0.33 | 0.7 | 0.98 | center | 355°
Mf41 | SMART24 | 2016-06-16 | 2016-11-03 | DAS off - Battery below 11.3 V. Stomp test showed weak signal (when powered with fresh battery) | 2188 |  | 92 | 2.3 | 11/1-11/3 | Voltage dopped to 11.3 V on 11/1. Never recovered | 0.77 | 2 | 2.6 | center | N=N
Mf54 | SMART24 | 2016-06-17 | 2016-11-03 | Puffy fiberglass insulation | 2234 |  | 95 | 3.54 |  |  | -1.1 | 5.2 | 3.7 | center | 008°
Mf61 | SMART24 | 2016-06-17 | 2016-11-03 |  | 1848 |  | 78 | 2.63 | 08/01-08/19 | Site mobilized late | -3.8 | 4.4 | 3.1 | center | N=N
Mf74 | SMART24 | 2016-06-17 | 2016-11-01 | Foam insulaton sleeve (not sticky back) | 2230 |  | 93 | 3.22 |  |  | -0.9 | -2 | 2.9 | center | N=N
Mf77 | SMART24 | 2016-06-17 | 2016-11-01 | DAS off - Battery below 11.3 V | 1996 |  | 82 | 2.85 | 10/23-11/3 | Voltage dopped to 11.3 V on 10/23. Never recovered | -1.7 | 2.2 | 1.5 | center | N=N
Mf79 | RT130 | 2016-06-17 | 2016-11-01 | Mice in rocks above vault | 751 |  | 75 | 4.23 | 8/1-8/19 | lots of "EXTERNAL CLOCK ERROR - SUSPENDING DRIFT CORRECTION" due to bad GPS or GPS location. Bad Power setup until 8/19 | -0.8 | 0.4 | 0.2 | WSW inside ring | 358°
Mf85 | RT130 | 2016-06-17 | 2016-11-01 | Sensor off pier and rotated - hopefully during demob. Rotation was 270 degrees, or 90 and sensor had been installed pointing south | 921 |  | 92 | 6.43 |  |  | -0.1 | 0.7 | 0.4 | ? | ? (N may be S)
Mf75 | RT130 | 2016-06-17 | 2016-11-01 | Very low battery, No GPS lock since restart, Channel 3 dead? | 951 | 1 corrupted file (deleted, missing 1 hr) | 95 | 5.59 | 10/30-11/1(end) | "TIMETAG ERROR" 215:00:24:00. 1.8 ms phase shift 260:16:44:22, and 3-4 other high phase shifts. "Missing ET Packets" at end of file. lots of "EXTERNAL CLOCK ERROR - SUSPENDING DRIFT CORRECTION" due to bad GPS or GPS location | -0.7 | 2.4 | -9.9 (weak signal in stomp test) | center | N=N
Mf21 | RT130 | 2016-06-16 | 2016-11-02 | Active logging(lumber) nearby | 941 |  | 94 | 4.53 |  |  | -0.7 | 1.7 | 1.6 | center | N=N
Mf12 | RT130 | 2016-06-16 | 2016-11-02 | Active logging(lumber) nearby | 941 |  | 94 | 6.03 |  |  | -0.1 | -0.3 | 0.1 | center | N=N
Mf15 | RT130 | 2016-06-17 | 2016-11-02 |  | 941 |  | 94 |  |  | a few "EXTERNAL CLOCK ERROR - SUSPENDING DRIFT CORRECTION" due to bad GPS or GPS location | 0.1 | 0.3 | 0.2 | center | N=N
Mf42 | RT130 | 2016-06-14 | 2016-11-03 | Puffy fiberglass insulation | 951 |  | 95 | 6.29 |  | "DSP CLOCK SET" 233:01:00:42 | 0.2 | 0.1 | 0 | W inside ring | 002°
Mf72 | RT130 | 2016-06-16 | 2016-11-03 |  | 951 |  | 95 | 5.81 |  | a few "EXTERNAL CLOCK ERROR - SUSPENDING DRIFT CORRECTION" due to bad GPS or GPS location | -0.3 | 1 | 1 | SW inside ring | N=N
Mf00 | RT130 | 2016-06-15 | 2016-11-03 | DAS Off - Battery below 12 V Soggy, puffy fiberglass insulation. | 861 |  | 95 | 5.21 | 10/24-11/3(end) | a few "EXTERNAL CLOCK ERROR - SUSPENDING DRIFT CORRECTION" due to bad GPS or GPS location | -1.1 | 3.8 | 0.3 | SW crossing ring | 004°
Mf64 | RT130 | 2016-06-17 | 2016-11-03 | Action-packer half full of water | 951 |  | 95 | 5.51 |  | 11 ms phase shift 238:11:42:25. A few "EXTERNAL CLOCK ERROR - SUSPENDING DRIFT CORRECTION" due to bad GPS or GPS location | -2.7 | 2.4 | 1.4 | NW inside ring | N=N
Mf68 | RT130 | 2016-06-17 | 2016-11-04 |  | 961 |  | 96 | 5.33 |  |  | 0.5 | 1.9 | 0.2 | SE inside ring | N=N
Vault Insulation was foam with sticky back adherred to plastic vault unless noted